## APS
JP PO NO. | Purchasing Document | APS/ MFG | Item | Net price | Document Date | Material | Short Text | Order Quantity | Order Unit | Delivered (qty) | Still to be delivered (qty) | Due Delivery Date | Delivered from office | Remark
| 151621853 | APS | 10 | 71648.8 | 15.05.2025 | 630059 | Cement Hop. Bellow_Silic_ dia 205x4x400mm | 15 | PCS | 15 | 0 | 14.06.2025 | 20/6/25
| 151621853 | APS | 20 | 67708.2 | 15.05.2025 | 632215 | Bellow_Butterfly-Valve_31 0x4x400mm | 10 | PCS | 10 | 0 | 14.06.2025 | 2025-12-07
| 151621862 | APS | 10 | 99367.8 | 15.05.2025 | 616026 | Screw Conveyor Bellow_Dia 224x4x500mm | 15 | PCS | 15 | 0 | 14.06.2025 | 11.6.25
| 151634177 | APS | 10 | 60888 | 12.06.2025 | 713141 | Discharge chute bellow Ø500x4x500 | 4 | PCS | 4 | 0 | 12.07.2025 | 20/6/25 | 1 replacement forwaarded to putzs might get replaced again 12.7.25
Namrata A 201 | 151642309 | APS | 10 | 76947.8 | 02.07.2025 | 616039 | Discharge Chute Bellow_Di a 500x4x240mm | 10 | PCS | 10 | 0 | 01.08.2025 |  | (2 replacement) 3 qty ordered on 3/7/25
| 151642309 | APS | 20 | 41949 | 02.07.2025 | 646872 | Water Bellow_BP60_Dia 170 x4x300mm | 10 | PCS | 10 | 0 | 01.08.2025
| 151642309 | APS | 30 | 67708.4 | 02.07.2025 | 632215 | Bellow_Butterfly-Valve_31 0x4x400mm | 10 | PCS | 10 | 0 | 01.08.2025
| 151659369 | APS | 10 | 85508.65 | 12.08.2025 | 615698 | Screw Conveyor Bellow_Dia 174x4x5 | 15 | PCS |  | 15 | 11.09.2025
| 151659369 | APS | 20 | 66245.2 | 12.08.2025 | 616026 | Screw Conveyor Bellow_Dia 224x4x500mm | 10 | PCS |  | 10 | 11.09.2025
[6 empty] | 713141 | Discharge chute bellow Ø500x4x500 | 1 | PCS
missing item received on 23.7.25

## MFG
JP PO NO. | Purchasing Document | APS/ MFG | Item | Net price | Document Date | Material | Short Text | Order Quantity | Order Unit | Delivered (qty) | Still to be delivered (qty) | Price per unit | Open order | Putz DUE Delivery Date | Delivery Date From Store | REMARK
| 151517683 | MFG | 70 | 2643.2 | 02.09.2024 | 649868 | Clamp for BP bellow Dia 310mm | 20 | PCS | 0 | 20 |  |  | 17.10.2024
| 151525288 | MFG | 50 | 1321.6 | 23.09.2024 | 649868 | Clamp for BP bellow Dia 310mm | 10 | PCS | 0 | 10 |  |  | 07.11.2024
| 151562990 | MFG | 10 | 53100 | 04.01.2025 | 719031 | Dell OptiPlex 3080 Tower | 1 | PCS | 0 | 1 |  |  | 24.01.2025
| 151566200 | MFG | 10 | 176982.3 | 10.01.2025 | 719381 | Monochrom laserjet printe rCanonLBP6030BJ | 15 | PCS | 0 | 15 |  |  | 27.01.2025 |  | need to amend from 15 qty to 20 qty
| 151566200 | MFG | 60 | 66245.2 | 10.01.2025 | 616026 | Screw Conveyor Bellow_Dia 224x4x500mm | 10 | PCS | 10 | 0 |  |  | 07.04.2025 |  | 1 replacement delivered on 11.6.25
| 151575274 | MFG | 10 | 176982.3 | 29.01.2025 | 719381 | Monochrom laserjet printerCanonLBP6030BJ | 15 | PCS |  | 15 |  |  | 19.02.2025
[6 empty] | 724214 | PC UPS | 2 | PCS | 2 | 0 |  |  |  | 21/04/2025
| 151611321 | MFG | 10 | 22372.8 | 18.04.2025 | 716663 | BELLOW F. water hopper MT 1.0 IB | 10 | PCS | 10 | 0 | 1896 |  | 08.05.2025 | 19/5/25
| 151611321 | MFG | 20 | 141458.4 | 18.04.2025 | 716334 | Bearing f. Take up Housin g UCT 215 | 24 | PCS | 24 | 0 | 4995 |  | 08.05.2025 | 2025-06-05
| 151611321 | MFG | 30 | 80004 | 18.04.2025 | 695947 | ROD END 20MM | 120 | PCS | 120 | 0 | 565 |  | 16.05.2025 | 2025-06-05
| 151611321 | MFG | 40 | 76548.48 | 18.04.2025 | 687254 | BEARING_TAKE UP HOUSING_U CT210 | 34 | PCS | 34 | 0 | 1908 |  | 02.06.2025 | 2025-06-05
| 151611321 | MFG | 50 | 99757.2 | 18.04.2025 | 635656 | Cement_Dust_BP60_Dia 150 flexible | 30 | M | 30 | 0 | 2818 |  | 02.06.2025 | 19/5/25
| 151611321 | MFG | 60 | 95532.8 | 18.04.2025 | 630059 | Cement Hop. Bellow_Silic_ dia 205x4x400mm | 20 | PCS | 20 | 0 | 4048 |  | 02.06.2025 | 2025-06-05 | 9 qty on 19/5/25
bal 15 qty closed | 151611321 | MFG | 70 | 307791.2 | 18.04.2025 | 616039 | Discharge Chute Bellow_Di a 500x4x240mm | 40 | PCS | 25 | 15 | 6521 | 16 qty on 11.6.25 | 02.06.2025 | 2025-06-05 | 8 qty on 19/5/25 and 16 qty on 11.6.25 | closed
| 151611321 | MFG | 80 | 231858.2 | 18.04.2025 | 616026 | Screw Conveyor Bellow_Dia 224x4x50 | 35 | PCS | 35 | 0 | 5614 | 15 | 16.07.2025 | 2025-06-05 | 14 on 19/5/25 and 5 qty on 11.6.25 & 15 qty on 11/7/25
| 151612151 | MFG | 10 | 5876.4 | 22.04.2025 | 724214 | PC UPS | 2 | PCS | 2 | 0
| 151618200 | MFG | 10 | 49088 | 07.05.2025 | 780236 | Bellow Butterfly-Valve 310x4x290mm | 10 | PCS | 10 | 0 |  |  | 06.06.2025 | 2025-01-08 | 2qty replacement
| 151627175 | MFG | 10 | 8949.12 | 27.05.2025 | 716663 | BELLOW F. water hopper MT 1.0 IBC | 4 | PCS | 4 | 0 | 1896 |  | 19.06.2025 | 20/6/25
| 151627175 | MFG | 20 | 58941 | 27.05.2025 | 716334 | Bearing f. Take up Housin g UCT 215 | 10 | PCS | 10 | 0 | 4995 |  | 19.06.2025 | 11.6.25
| 151627175 | MFG | 30 | 73337 | 27.05.2025 | 695947 | ROD END 20MM | 110 | PCS | 110 | 0 | 565 |  | 24.06.2025 | 11.6.25
| 151627175 | MFG | 40 | 112572 | 27.05.2025 | 687254 | BEARING_TAKE UP HOUSING_U CT210 | 50 | PCS | 50 | 0 | 1908 |  | 11.07.2025 | 11.6.25
| 151627175 | MFG | 50 | 191064.8 | 27.05.2025 | 630059 | Cement Hop. Bellow_Silic_ dia 205x4x400mm | 40 | PCS | 40 | 0 | 4048 | 40 | 11.07.2025 | 20/6/25 | 15 qty on 11/7/2025
| 151627175 | MFG | 60 | 192369.25 | 27.05.2025 | 616039 | Discharge Chute Bellow_Di a 500x4x240mm | 25 | PCS | 25 | 0 | 6521 | 25 | 11.07.2025 | 20/6/25 | 9 qty on 11/7/2025
| 151641682 | MFG | 10 | 117988.2 | 01.07.2025 | 719381 | Monochrom laserjet printe rCanonLBP6030BJ | 10 | PCS |  | 10 |  |  | 22.07.2025
CNZ 203 | 151641682 | MFG | 20 | 66670 | 01.07.2025 | 695947 | ROD END 20MM | 100 | PCS | 100 | 0 |  |  | 29.07.2025 | 2025-11-07
Namrata M 202 | 151641682 | MFG | 30 | 15611.4 | 01.07.2025 | 663093 | Screw conv. Bellow_Dia278 x500lg_MT3.0 | 2 | PCS | 1 | 1 |  |  | 29.09.2025
| 151641682 | MFG | 40 | 3964.8 | 01.07.2025 | 649868 | Clamp for BP bellow Dia 3 10mm | 30 | PCS |  | 30 |  |  | 16.08.2025
Namrata M 202 | 151641682 | MFG | 50 | 41949 | 01.07.2025 | 646872 | Water Bellow_BP60_Dia 170 x4x300mm | 10 | PCS | 7 | 3 |  |  | 14.08.2025
Vantage 204 | 151641682 | MFG | 60 | 99757.2 | 01.07.2025 | 635656 | Cement_Dust_BP60_Dia 150 flexible | 30 | PCS | 30 | 0 |  |  | 16.08.2025 | 2025-01-08
| 151641682 | MFG | 70 | 157300.4 | 01.07.2025 | 635655 | DUSTFILTR BP60 DIA250mm F LEXIBLE | 30 | PCS | 30 | 0 |  |  | 16.08.2025 | 2025-01-08
Namrata M 202 | 151641682 | MFG | 80 | 54166.72 | 01.07.2025 | 632215 | Bellow_Butterfly-Valve_31 0x4x400mm | 8 | PCS | 1 | 7 |  |  | 16.08.2025
| 151641682 | MFG | 90 | 86118.76 | 01.07.2025 | 616026 | Screw Conveyor Bellow_Dia 224x4x500mm | 13 | PCS | 13 | 0 |  |  | 29.09.2025
| 151639440 | MFG | 10 | 66080 | 26.06.2025 | 772264 | SPRAY NOZZLE D 12.6 120 D EG SS | 50 | PCS | 50 | 0 |  |  | 26.07.2025 | 2025-01-08 | Amanded from 20 to 50 qty
ORAL | 151644665 | MFG | 10 | 17629.2 | 08.07.2025 | 724214 | PC UPS | 6 | PCS | 6 | 0 |  |  | 05.08.2025 | 2025-11-07
ORAL | 151644666 | MFG | 10 | 11752.8 | 08.07.2025 | 724214 | PC UPS | 4 | PCS | 4 | 0 |  |  | 05.08.2025 | 2025-11-07

## Pending to place order
Purchasing Document | APS/ MFG | Item | Net price | Document Date | Material | Short Text | Order Quantity | Order Unit | Delivered (qty) | Still to be delivered (qty) | Putz DUE Delivery Date | Delivery Date From Store | REMARK
151517683 | MFG | 70 | 2643.2 | 02.09.2024 | 649868 | Clamp for BP bellow Dia 310mm | 20 | PCS |  | 0 | 20 |  | 17.10.2024
151525288 | MFG | 50 | 1321.6 | 23.09.2024 | 649868 | Clamp for BP bellow Dia 310mm | 10 | PCS |  | 0 | 10 |  | 07.11.2024
151562990 | MFG | 10 | 53100 | 04.01.2025 | 719031 | Dell OptiPlex 3080 Tower | 1 | PCS |  | 0 | 1 |  | 24.01.2025
151566200 | MFG | 10 | 176982.3 | 10.01.2025 | 719381 | Monochrom laserjet printe rCanonLBP6030BJ | 15 | PCS |  | 0 | 15 |  | 27.01.2025 | need to amend from 15 qty to 20 qty
151575274 | MFG | 10 | 176982.3 | 29.01.2025 | 719381 | Monochrom laserjet printerCanonLBP6030BJ | 15 | PCS |  |  | 15 |  | 19.02.2025
151641682 | MFG | 10 | 117988.2 | 01.07.2025 | 719381 | Monochrom laserjet printe rCanonLBP6030BJ | 10 | PCS |  |  |  |  | 22.07.2025
151641682 | MFG | 40 | 3964.8 | 01.07.2025 | 649868 | Clamp for BP bellow Dia 3 10mm | 30 | PCS |  |  |  |  | 16.08.2025

## PENDIND SUPPLY
APS |  |  |  |  | Pending
JP PO NO. | Purchasing Document | APS/ MFG | Item | Net price | Document Date | Material | Short Text | Order Quantity | Order Unit | Delivered (qty) | Still to be delivered (qty) | Due Delivery Date | Delivered from office | Remark
Namrata A 201 | 151642309 | APS | 10 | 76947.8 | 02.07.2025 | 616039 | Discharge Chute Bellow_Di a 500x4x240mm | 10 | PCS | 5 | 5 | 01.08.2025 |  | (2 replacement) 3 qty ordered on 3/7/25
| 151642309 | APS | 20 | 41949 | 02.07.2025 | 646872 | Water Bellow_BP60_Dia 170 x4x300mm | 10 | PCS |  | 10 | 01.08.2025
| 151642309 | APS | 30 | 67708.4 | 02.07.2025 | 632215 | Bellow_Butterfly-Valve_31 0x4x400mm | 10 | PCS |  | 10 | 01.08.2025
MFG | [5 empty] | Pending
JP PO NO. | Purchasing Document | APS/ MFG | Item | Net price | Document Date | Material | Short Text | Order Quantity | Order Unit | Delivered (qty) | Still to be delivered (qty) | Price per unit | Open order | Putz DUE Delivery Date | Delivery Date From Store | REMARK
| 151517683 | MFG | 70 | 2643.2 | 02.09.2024 | 649868 | Clamp for BP bellow Dia 310mm | 20 | PCS | 0 | 20 |  |  | 17.10.2024
| 151525288 | MFG | 50 | 1321.6 | 23.09.2024 | 649868 | Clamp for BP bellow Dia 310mm | 10 | PCS | 0 | 10 |  |  | 07.11.2024
| 151562990 | MFG | 10 | 53100 | 04.01.2025 | 719031 | Dell OptiPlex 3080 Tower | 1 | PCS | 0 | 1 |  |  | 24.01.2025
| 151566200 | MFG | 10 | 176982.3 | 10.01.2025 | 719381 | Monochrom laserjet printe rCanonLBP6030BJ | 15 | PCS | 0 | 15 |  |  | 27.01.2025 |  | need to amend from 15 qty to 20 qty
| 151575274 | MFG | 10 | 176982.3 | 29.01.2025 | 719381 | Monochrom laserjet printerCanonLBP6030BJ | 15 | PCS |  | 15 |  |  | 19.02.2025
| 151611321 | MFG | 70 | 307791.2 | 18.04.2025 | 616039 | Discharge Chute Bellow_Di a 500x4x240mm | 40 | PCS | 25 | 15 | 6521 | 16 qty on 11.6.25 | 02.06.2025 | 2025-06-05 | 8 qty on 19/5/25 and 16 qty on 11.6.25 | closed
| 151618200 | MFG | 10 | 49088 | 07.05.2025 | 780236 | Bellow Butterfly-Valve 310x4x290mm | 10 | PCS | 8 | 2 |  |  | 06.06.2025 |  | 2qty replacement
| 151641682 | MFG | 10 | 117988.2 | 01.07.2025 | 719381 | Monochrom laserjet printe rCanonLBP6030BJ | 10 | PCS |  | 10 |  |  | 22.07.2025
Namrata M 202 | 151641682 | MFG | 30 | 15611.4 | 01.07.2025 | 663093 | Screw conv. Bellow_Dia278 x500lg_MT3.0 | 2 | PCS |  | 2 |  |  | 29.09.2025
| 151641682 | MFG | 40 | 3964.8 | 01.07.2025 | 649868 | Clamp for BP bellow Dia 3 10mm | 30 | PCS |  | 30 |  |  | 16.08.2025
Namrata M 202 | 151641682 | MFG | 50 | 41949 | 01.07.2025 | 646872 | Water Bellow_BP60_Dia 170 x4x300mm | 10 | PCS |  | 10 |  |  | 14.08.2025
Vantage 204 | 151641682 | MFG | 60 | 99757.2 | 01.07.2025 | 635656 | Cement_Dust_BP60_Dia 150 flexible | 30 | PCS |  | 30 |  |  | 16.08.2025
| 151641682 | MFG | 70 | 157300.4 | 01.07.2025 | 635655 | DUSTFILTR BP60 DIA250mm F LEXIBLE | 30 | PCS |  | 30 |  |  | 16.08.2025
Namrata M 202 | 151641682 | MFG | 80 | 54166.72 | 01.07.2025 | 632215 | Bellow_Butterfly-Valve_31 0x4x400mm | 8 | PCS |  | 8 |  |  | 16.08.2025
| 151641682 | MFG | 90 | 86118.76 | 01.07.2025 | 616026 | Screw Conveyor Bellow_Dia 224x4x500mm | 13 | PCS |  | 13 |  |  | 29.09.2025
| 151639440 | MFG | 10 | 66080 | 26.06.2025 | 772264 | SPRAY NOZZLE D 12.6 120 D EG SS | 50 | PCS |  | 50 |  |  | 26.07.2025 |  | Amanded from 20 to 50 qty

## Materials Vendor Details
Sr.no | Part no. | Description | Price | Vendor | Sales Price | Phone no. / Email ID | Email ID
1 | 716663 | BELLOW F. water hopper MT1.0 IBC | 750 | Namrata | 1896 | Namrata main no.
2 | 663092 | Cement Bellow_Dia330x200lg_MT3.0 | 1450 | Namrata | 5130 | 8898278098
3 | 663093 | Screw conv. Bellow_Dia278x500lg_MT3.0 | 2800 | Namrata | 6615 | namratarubberproduct@gmail.com | namratarubberproduct@gmail.com
4 | 646872 | Water Bellow_BP60_Dia 170x4x300mm | 1225 | Namrata | 3555
5 | 663091 | Water Bellow_Dia173x200 lg_MT3.0 | 1050 | Namrata | 3510 | Trupti
6 | 663094 | Discharge hopper bellow_Dia605x600_MT3.0 | 5400/6000 | Namrata | 10602 | 9867838855 | 5400
7 | 615698 | Screw Conveyor Bellow_Dia174x4x500mm | 1880 | Namrata | 4831
8 | 616026 | Screw Conveyor Bellow_Dia224x4x500mm | 2245 | Namrata | 5614
9 | 630059 | Cement Hop. Bellow_Silic_dia 205x4x400mm | 1725 | Namrata | 4048
10 | 616039 | Discharge Chute Bellow_Dia 500x4x240mm | 3100 | Namrata | 6521
11 | 632215 | Bellow_Butterfly-Valve_31 0x4x400mm | 2270 | Namrata | 5738
12 | 713141 | Discharge chute bellow Ø500x4x500 | 6000 | Namrata | 12900
13 | 780236 | Bellow Butterfly-Valve 310x4x290mm | 1700 | Namrata | 4160 | 4750 | sir email rate is 4750
14 | 716334 | Bearing f. Take up Housing UCT 215 | 2950 | CNZ | 4995 | 8469008882
15 | 695947 | ROD END 20MM | 445 | CNZ | 565
16 | 687254 | BEARING_TAKE UP HOUSING_UCT210 | 1250 | CNZ | 1908
17 | 635655 | DUSTFILTR BP60 DIA250mm FLEXIBLE | 1170 | Vantage Rubber Co. | 4726 | 8383036214
18 | 725828 | Cement dust collector bellow dia245mm
19 | 635656 | Cement_Dust_BP60_Dia 150flexible | 340 | Vantage Rubber Co. | 2818 | 9810099146
20 | 777097 | Dia 150mm flexible grey PVC hose f. PRV | 702 | Vantage | 5738 | 9810099146
21 | 649868 | Clamp for BP bellow Dia 310mm |  | Vantage-120/ Local | 112 | vantagerubber@yahoo.co.in | vantagerubber@yahoo.co.in
22 | 615181 | INDUSTRIAL BELL_225mm |  | Max International
23 | 668330 | Rollling bearing NUKR47 |  | V M Traders | 5738
24 | 772264 | SPRAY NOZZLE D 12.6 120 DEG SS | 780 | Spraynoz Technologies | 2800
25 | 681149 | Computer Screen 19", HDMICable, 4GB RAM |  | Dell
26 | 615840 | Control Room Desk_1000×500×750 |  | Nilkand/ AI Furniture
27 | 724214 | PC UPS | 9067.8 | Ingram/ Delta | 2490
28 | 719381 | Monochrom laserjet printerCanonLBP6030BJ |  | Pritvi/Jushi | 9999
29 | 719031 | Dell OptiPlex 3080 Tower |  |  | 45000
30 | 615000 | Admixture Tank_15 ltrs
31 | 662351 | Admixture Tank 30 Ltrs |  |  | 24050
32 | 615863 | Control Room Spike Board | 120-170 | Hatley/ shri hari | 600 | 9271006894 / 8806406674 / 9130067500 / | hatleytechnologies@gmail.com
hatleytechnologies@gmail.com
33 |  | PP Sheet White Colour Top Plate OD 350 x 25mm THK | 1695 | Om package |  | 9921223437 | ompacking123@gmail.com
34 |  | PP Sheet White Colour Bottom Plate OD 350 x 25mm THK | 1695 | Om package |  | ompacking123@gmail.com
35 |  | Acrylic Pipe clear transparent size 300mm x 5mm x 500mm | 2225 | Parul Corporation |  | 9825061951 | parindoshi@gmail.com
36 | [5 empty] | parindoshi@gmail.com
37 |  | S S STUD 304 630mm long m12 (12mm thick) stud with Threading on both sides 55 mm with nuts and 2 washers | 330 | M R Steel |  | 9820503072 / 9833631987 | mrsteel2006@gmail.com
38 | [5 empty] | mrsteel2006@gmail.com
39 |  | Spray Nozel with flow capacity GPM at 40 PSI should be 39.85 presure bar should be maintained as per attachemnt | 5800 | Spraynoz Technologies
40 |  | Rubber o ring 5mm thick 300mm od 290mm id |  | Asha Enterprises
41 |  | Control Room Desk Leo | 241.53 | A1 Furniture
42 |  | Vostro Desktop 3710 |  | Dell
43 |  | Dell 22 Monitor - E2222H |  | Dell
44 |  | NRV Valv |  | AK Traders